## CynLr_EPM_PoC_Asana
Task ID | Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent task | Blocked By (Dependencies) | Blocking (Dependencies)
1218521240190061 | 2026-09-16 |  | 2026-09-16 | Define Phase 1 Experiment | Phase 1 — Track Moving Objects | [5 empty] | Objective: Define the Phase 1 experiment for tracking moving objects on a conveyor using the robot and sensing system. Scope: Establish the objects, operating conditions, tracking scenarios, and measurable performance criteria required to evaluate the tracking capability. Key Questions: What objects and object characteristics must be tracked? Under what conveyor and operating conditions will the experiment run? What tracking scenarios and variations need to be tested? How will tracking performance be measured? What conditions must be satisfied before the experiment plan is approved? Expected Output: A documented and approved Phase 1 experiment plan covering object characteristics, conveyor conditions, tracking scenarios, and performance criteria. Completion Criteria: The experiment scope, test conditions, scenarios, and measurable success criteria are documented, reviewed, and approved before implementation begins. | CynLr_EPM_PoC_Asana |  |  | Verify Robot and Conveyor Availability
1218521240190097 | 2026-09-16 |  | 2026-09-16 | Define Object Characteristics | [8 empty] | Define Phase 1 Experiment
1218521240190098 | 2026-09-16 |  | 2026-09-16 | Define Conveyor Conditions | [8 empty] | Define Phase 1 Experiment
1218521240190099 | 2026-09-16 |  | 2026-09-16 | Define Tracking Scenarios | [8 empty] | Define Phase 1 Experiment
1218521240190100 | 2026-09-16 |  | 2026-09-16 | Define Performance Criteria | [8 empty] | Define Phase 1 Experiment
1218521240190101 | 2026-09-16 |  | 2026-09-16 | Approve Experiment Plan | [8 empty] | Define Phase 1 Experiment
1218521240190063 | 2026-09-16 |  | 2026-09-16 | Verify Robot and Conveyor Availability | Phase 1 — Track Moving Objects | [5 empty] | Objective: Confirm that the robot, conveyor, camera, workspace, and other required resources are available and suitable for the Phase 1 tracking experiment. Scope: Identify the hardware and environmental conditions required for the experiment, verify their availability, and record any constraints that may affect execution. Key Questions: Is the required robot available and operational? Is the conveyor available and suitable for the planned experiments? Is the required camera and sensing equipment available? Is the workspace ready for safe and repeatable testing? Are there any hardware, software, or access constraints? Expected Output: A confirmed resource-availability checklist and a documented list of setup constraints. Completion Criteria: Required resources are verified, missing items or constraints are recorded, and the setup is confirmed ready for the next preparation activities. | CynLr_EPM_PoC_Asana |  | Define Phase 1 Experiment | Prepare Camera and Sensing Setup
1218521240190102 | 2026-09-16 |  | 2026-09-16 | Confirm Robot Availability | [8 empty] | Verify Robot and Conveyor Availability
1218521240190103 | 2026-09-16 |  | 2026-09-16 | Confirm Conveyor Availability | [8 empty] | Verify Robot and Conveyor Availability
1218521240190104 | 2026-09-16 |  | 2026-09-16 | Confirm Camera Availability | [8 empty] | Verify Robot and Conveyor Availability
1218521240190105 | 2026-09-16 |  | 2026-09-16 | Confirm Workspace Availability | [8 empty] | Verify Robot and Conveyor Availability
1218521240190106 | 2026-09-16 |  | 2026-09-16 | Record Setup Constraints | [8 empty] | Verify Robot and Conveyor Availability
1218521240190065 | 2026-09-16 |  | 2026-09-16 | Prepare Camera and Sensing Setup | Phase 1 — Track Moving Objects | [5 empty] | Objective: Prepare the camera and sensing system required to observe and track moving objects during the Phase 1 experiment. Scope: Select and install the appropriate camera configuration, connect the sensing equipment, verify data capture, and confirm that the setup is ready for calibration and tracking development. Key Questions: What camera configuration is suitable for the experiment? Where should the camera be positioned? Is the camera connected correctly to the system? Is the captured data usable for tracking? Are there any field-of-view, lighting, connectivity, or mounting constraints? Expected Output: A functional camera and sensing setup capable of capturing the required data for the Phase 1 experiment. Completion Criteria: The camera and sensing equipment are installed, connected, tested, and confirmed ready for calibration and tracking development.- | CynLr_EPM_PoC_Asana |  | Verify Robot and Conveyor Availability | Calibrate Camera and Coordinate System
1218521240190107 | 2026-09-16 |  | 2026-09-16 | Select Camera Configuration | [8 empty] | Prepare Camera and Sensing Setup
1218521240190109 | 2026-09-16 |  | 2026-09-16 | Mount Camera | [8 empty] | Prepare Camera and Sensing Setup
1218521240190110 | 2026-09-16 |  | 2026-09-16 | Connect Camera to System | [8 empty] | Prepare Camera and Sensing Setup
1218521240190111 | 2026-09-16 |  | 2026-09-16 | Verify Data Capture | [8 empty] | Prepare Camera and Sensing Setup
1218521240190112 | 2026-09-16 |  | 2026-09-16 | Confirm Sensing Setup Readiness | [8 empty] | Prepare Camera and Sensing Setup
1218521240190067 | 2026-09-16 |  | 2026-09-16 | Calibrate Camera and Coordinate System | Phase 1 — Track Moving Objects | [5 empty] | Objective: Establish the relationship between the camera, conveyor, robot, and workspace coordinate systems. Scope: Perform camera calibration, define the workspace coordinate frame, and verify that observed object positions can be expressed in the coordinate system required for tracking and robot integration. Key Questions: • What coordinate system will be used? • How will the camera be calibrated? • How will camera coordinates relate to conveyor and robot coordinates? • What calibration accuracy is required? • How will calibration accuracy be verified? Expected Output: A calibrated camera and documented coordinate-system relationship suitable for object tracking and robot integration. Completion Criteria: Calibration is completed, coordinate transformations are documented, and the resulting accuracy is verified against the experiment requirements. | CynLr_EPM_PoC_Asana |  | Prepare Camera and Sensing Setup | Develop Object Tracking Capability
1218521240190113 | 2026-09-16 |  | 2026-09-16 | Perform Camera Calibration | [8 empty] | Calibrate Camera and Coordinate System
1218521240190114 | 2026-09-16 |  | 2026-09-16 | Establish Coordinate Frames | [8 empty] | Calibrate Camera and Coordinate System
1218521240190115 | 2026-09-16 |  | 2026-09-16 | Verify Camera-to-Robot Relationship | [8 empty] | Calibrate Camera and Coordinate System
1218521240190116 | 2026-09-16 |  | 2026-09-16 | Validate Calibration | [8 empty] | Calibrate Camera and Coordinate System
1218521240190069 | 2026-09-16 |  | 2026-09-16 | Develop Object Tracking Capability | Phase 1 — Track Moving Objects | [5 empty] | Objective: Develop the capability to detect and track moving objects during the Phase 1 experiment. Scope: Implement or configure the tracking pipeline, process camera data, identify objects, estimate their positions over time, and evaluate tracking performance under the defined experiment conditions. Key Questions: • How will objects be detected? • How will object identity be maintained across frames? • How will object position and motion be estimated? • How will tracking failures be handled? • What performance metrics will be measured? Expected Output: A functioning object-tracking capability suitable for integration with the robot. Completion Criteria: Objects can be detected and tracked under the defined test conditions, and tracking performance is measured against the experiment criteria. | CynLr_EPM_PoC_Asana |  | Calibrate Camera and Coordinate System | Integrate Tracking Output with Robot
1218521240190117 | 2026-09-16 |  | 2026-09-16 | Define Tracking Approach | [8 empty] | Develop Object Tracking Capability
1218521240190118 | 2026-09-16 |  | 2026-09-16 | Implement Object Detection | [8 empty] | Develop Object Tracking Capability
1218521240190119 | 2026-09-16 |  | 2026-09-16 | Implement Position Estimation | [8 empty] | Develop Object Tracking Capability
1218521240190120 | 2026-09-16 |  | 2026-09-16 | Implement Tracking Logic | [8 empty] | Develop Object Tracking Capability
1218521240190121 | 2026-09-16 |  | 2026-09-16 | Test Tracking Output | [8 empty] | Develop Object Tracking Capability
1218521240190071 | 2026-09-16 |  | 2026-09-16 | Integrate Tracking Output with Robot | Phase 1 — Track Moving Objects | [5 empty] | Objective: Connect the object-tracking output to the robot system so that tracked object information can be used by the robot. Scope: Define the communication interface, map tracking coordinates to the robot coordinate system, transmit object position data, and verify that the robot can receive and interpret the tracking output. Key Questions: • What data must be transmitted to the robot? • What communication interface will be used? • How will coordinates be transformed? • What update rate and latency are required? • How will communication errors be handled? Expected Output: A verified interface between the tracking system and the robot. Completion Criteria: The robot receives valid tracking data in the required coordinate system and the interface operates reliably under test conditions. | CynLr_EPM_PoC_Asana |  | Develop Object Tracking Capability | Execute Tracking Experiments
1218521240190122 | 2026-09-16 |  | 2026-09-16 | Define Robot Interface | [8 empty] | Integrate Tracking Output with Robot
1218521240190123 | 2026-09-16 |  | 2026-09-16 | Connect Tracking Output | [8 empty] | Integrate Tracking Output with Robot
1218521240190124 | 2026-09-16 |  | 2026-09-16 | Verify Target Position Transfer | [8 empty] | Integrate Tracking Output with Robot
1218521240190125 | 2026-09-16 |  | 2026-09-16 | Test Robot Response | [8 empty] | Integrate Tracking Output with Robot
1218521240190126 | 2026-09-16 |  | 2026-09-16 | Validate Integrated Tracking | [8 empty] | Integrate Tracking Output with Robot
1218521240190073 | 2026-09-16 |  | 2026-09-16 | Execute Tracking Experiments | Phase 1 — Track Moving Objects | [5 empty] | Objective: Execute the defined Phase 1 experiments to evaluate moving-object tracking performance. Scope: Run the planned tracking scenarios, collect experimental data, record operating conditions, and document successful and unsuccessful trials. Expected Output: A complete experimental dataset and execution record. Completion Criteria: All planned scenarios are executed or deviations are documented, and the required measurements are collected. | CynLr_EPM_PoC_Asana |  | Integrate Tracking Output with Robot | Analyze Experiment Results
1218521240190127 | 2026-09-16 |  | 2026-09-16 | Prepare Test Scenarios | [8 empty] | Execute Tracking Experiments
1218521240190128 | 2026-09-16 |  | 2026-09-16 | Run Baseline Trials | [8 empty] | Execute Tracking Experiments
1218521240190129 | 2026-09-16 |  | 2026-09-16 | Run Variation Trials | [8 empty] | Execute Tracking Experiments
1218521240190130 | 2026-09-16 |  | 2026-09-16 | Run Repeatability Trials | [8 empty] | Execute Tracking Experiments
1218521240190131 | 2026-09-16 |  | 2026-09-16 | Record Results | [8 empty] | Execute Tracking Experiments
1218521240190075 | 2026-09-16 |  | 2026-09-16 | Analyze Experiment Results | Phase 1 — Track Moving Objects | [5 empty] | Objective: Analyze the Phase 1 experimental results and determine whether the tracking capability meets the defined requirements. Scope: Review tracking accuracy, reliability, latency, and failure cases using the collected experimental data. Expected Output: A documented analysis of tracking performance and identified improvement areas. Completion Criteria: Results are compared against the defined performance criteria and conclusions are documented. | CynLr_EPM_PoC_Asana |  | Execute Tracking Experiments | Conduct Phase 1 Review
1218521240190132 | 2026-09-16 |  | 2026-09-16 | Analyze Tracking Accuracy | [8 empty] | Analyze Experiment Results
1218521240190133 | 2026-09-16 |  | 2026-09-16 | Analyze Latency | [8 empty] | Analyze Experiment Results
1218521240190134 | 2026-09-16 |  | 2026-09-16 | Analyze Failures | [8 empty] | Analyze Experiment Results
1218521240190135 | 2026-09-16 |  | 2026-09-16 | Identify Limitations | [8 empty] | Analyze Experiment Results
1218521240190136 | 2026-09-16 |  | 2026-09-16 | Prepare Results Summary | [8 empty] | Analyze Experiment Results
1218521240190077 | 2026-09-16 |  | 2026-09-18 | Conduct Phase 1 Review | Phase 1 — Track Moving Objects | [5 empty] | Objective: Review the Phase 1 results and determine readiness to proceed to Phase 2. Scope: Review experiment outcomes, tracking performance, unresolved issues, risks, and recommendations for the track-and-grasp phase. Expected Output: A Phase 1 review record with decisions and follow-up actions. Completion Criteria: Phase 1 results are reviewed, open issues are recorded, and the decision to proceed, revise, or repeat experiments is documented. | CynLr_EPM_PoC_Asana |  | Analyze Experiment Results | Review Overall PoC Results
1218521240190137 | 2026-09-16 |  | 2026-09-16 | Review Technical Results | [8 empty] | Conduct Phase 1 Review
1218521240190138 | 2026-09-16 |  | 2026-09-16 | Review Unresolved Risks | [8 empty] | Conduct Phase 1 Review
1218521240190139 | 2026-09-16 |  | 2026-09-16 | Review Readiness for Phase 2 | [8 empty] | Conduct Phase 1 Review
1218521240190140 | 2026-09-16 |  | 2026-09-16 | Record Go / No-Go / Revise Decision | [8 empty] | Conduct Phase 1 Review
1218521240190079 | 2026-09-16 |  | 2026-09-18 | Define Phase 2 Experiment | Phase 2 — Track & Grasp | [5 empty] | Objective: Define the Phase 2 experiment for tracking and grasping moving objects using the robot, RTU, and gripper or end-of-arm tooling. Scope: Establish the objects, operating conditions, tracking-and-grasping scenarios, and measurable performance criteria required to evaluate the integrated capability. Key Questions: • What objects must be tracked and grasped? • What are the conveyor and operating conditions? • What grasping scenarios need to be tested? • What role does the RTU play in the experiment? • How will grasping performance be measured? • What conditions must be satisfied before the experiment begins? Expected Output: A documented Phase 2 experiment plan covering object characteristics, operating conditions, tracking-and-grasping scenarios, and performance criteria. Completion Criteria: The experiment scope, test conditions, scenarios, and measurable success criteria are documented, reviewed, and approved before implementation begins. | CynLr_EPM_PoC_Asana |  |  | Confirm RTU and Robot Availability,Review Overall PoC Results
1218521240190157 | 2026-09-16 |  | 2026-09-16 | Define Object and Grasping Requirements | [8 empty] | Define Phase 2 Experiment
1218521240190158 | 2026-09-16 |  | 2026-09-16 | Define RTU Operating Conditions | [8 empty] | Define Phase 2 Experiment
1218521240190159 | 2026-09-16 |  | 2026-09-16 | Define Tracking-and-Grasping Scenarios | [8 empty] | Define Phase 2 Experiment
1218521240190160 | 2026-09-16 |  | 2026-09-16 | Define Grasping Performance Criteria | [8 empty] | Define Phase 2 Experiment
1218521240190161 | 2026-09-16 |  | 2026-09-16 | Approve Phase 2 Experiment Plan | [8 empty] | Define Phase 2 Experiment
1218521240190081 | 2026-09-16 |  | 2026-09-16 | Confirm RTU and Robot Availability | Phase 2 — Track & Grasp | [5 empty] | Objective: Confirm that the robot, RTU, and supporting equipment required for Phase 2 are available and suitable for the planned tracking-and-grasping experiments. Scope: Verify equipment availability, operational status, workspace readiness, and compatibility with the Phase 2 experiment requirements. Key Questions: • Is the required robot available and operational? • Is the RTU available and compatible with the robot? • Is the gripper or end-of-arm tooling available? • Are the required communication interfaces available? • Is the workspace ready for safe and repeatable testing? • Are there any hardware, software, or access constraints? Expected Output: A confirmed resource-availability checklist and a documented list of setup constraints. Completion Criteria: Required resources are verified, missing items or constraints are recorded, and the setup is confirmed ready for RTU integration. | CynLr_EPM_PoC_Asana |  | Define Phase 2 Experiment | Prepare RTU Integration Setup
1218521240190162 | 2026-09-16 |  | 2026-09-16 | Verify Robot Availability | [8 empty] | Confirm RTU and Robot Availability
1218521240190163 | 2026-09-16 |  | 2026-09-16 | Verify RTU Availability | [8 empty] | Confirm RTU and Robot Availability
1218521240190164 | 2026-09-16 |  | 2026-09-16 | Verify Gripper / End-of-Arm Tooling Availability | [8 empty] | Confirm RTU and Robot Availability
1218521240190165 | 2026-09-16 |  | 2026-09-16 | Verify Communication Interfaces | [8 empty] | Confirm RTU and Robot Availability
1218521240190166 | 2026-09-16 |  | 2026-09-16 | Confirm Workspace Readiness | [8 empty] | Confirm RTU and Robot Availability
1218521240190083 | 2026-09-16 |  | 2026-09-16 | Prepare RTU Integration Setup | Phase 2 — Track & Grasp | [5 empty] | Objective: Prepare the RTU and supporting interfaces required to integrate tracking information with the robot during Phase 2. Scope: Configure the RTU, establish communication with the robot and sensing system, and verify that the required data can be exchanged reliably. Key Questions: • What RTU configuration is required? • How will tracking data be received by the RTU? • How will the RTU communicate with the robot? • What data format and update rate are required? • Are the required interfaces and software available? • How will communication be tested? Expected Output: A configured RTU integration setup capable of receiving and exchanging the required tracking information. Completion Criteria: The RTU is configured, communication interfaces are established, and data exchange is verified before robot integration begins. | CynLr_EPM_PoC_Asana |  | Confirm RTU and Robot Availability | Integrate Robot and RTU
1218521240190167 | 2026-09-16 |  | 2026-09-16 | Define RTU Configuration | [8 empty] | Prepare RTU Integration Setup
1218521240190168 | 2026-09-16 |  | 2026-09-16 | Configure RTU | [8 empty] | Prepare RTU Integration Setup
1218521240190169 | 2026-09-16 |  | 2026-09-16 | Establish Communication Interfaces | [8 empty] | Prepare RTU Integration Setup
1218521240190170 | 2026-09-16 |  | 2026-09-16 | Configure Tracking Data Exchange | [8 empty] | Prepare RTU Integration Setup
1218521240190172 | 2026-09-16 |  | 2026-09-16 | Verify RTU Communication | [8 empty] | Prepare RTU Integration Setup
1218521240190085 | 2026-09-16 |  | 2026-09-16 | Integrate Robot and RTU | Phase 2 — Track & Grasp | [5 empty] | Objective: Establish communication and functional integration between the robot and RTU for Phase 2 tracking-and-grasping experiments. Scope: Connect the robot and RTU, configure the required control and data interfaces, and verify that tracking information can be used by the robot. Key Questions: • How will the robot and RTU communicate? • What tracking information must be transferred? • How will coordinate systems and reference frames be handled? • How will the robot respond to tracking updates? • What safety and control constraints apply? • How will the integration be validated? Expected Output: A functional robot–RTU integration capable of receiving and using tracking information. Completion Criteria: Robot–RTU communication is established, tracking data is exchanged correctly, and the integrated setup is ready for track-and-grasp development. | CynLr_EPM_PoC_Asana |  | Prepare RTU Integration Setup | Develop Track-and-Grasp Capability
1218521240190173 | 2026-09-16 |  | 2026-09-16 | Define Robot–RTU Interface | [8 empty] | Integrate Robot and RTU
1218521240190174 | 2026-09-16 |  | 2026-09-16 | Connect and Configure Robot–RTU Communication | [8 empty] | Integrate Robot and RTU
1218521240190175 | 2026-09-16 |  | 2026-09-16 | Verify Tracking Data and Robot Response | [8 empty] | Integrate Robot and RTU
1218521240190087 | 2026-09-16 |  | 2026-09-16 | Develop Track-and-Grasp Capability | Phase 2 — Track & Grasp | [5 empty] | Objective: Develop the capability to track moving objects and generate the information required for the robot to grasp them. Scope: Extend the Phase 1 tracking capability to support grasp-point estimation, motion prediction where required, and coordination between tracking and robot action. Key Questions: • How will the tracked object position be used for grasping? • How will the grasp point or grasp pose be determined? • Is motion prediction required? • How will tracking updates be synchronized with robot motion? • How will tracking errors affect grasping? • What conditions must be satisfied before a grasp is attempted? Expected Output: A working track-and-grasp capability that connects object tracking information to robot grasping actions. Completion Criteria: The system can track the target object, generate the required grasp information, and support controlled grasping trials. | CynLr_EPM_PoC_Asana |  | Integrate Robot and RTU | Integrate Gripper / End-of-Arm Tooling
1218521240190176 | 2026-09-16 |  | 2026-09-16 | Define Grasping Requirements | [8 empty] | Develop Track-and-Grasp Capability
1218521240190177 | 2026-09-16 |  | 2026-09-16 | Develop Grasp Planning and Timing Logic | [8 empty] | Develop Track-and-Grasp Capability
1218521240190178 | 2026-09-16 |  | 2026-09-16 | Test Track-and-Grasp Functionality | [8 empty] | Develop Track-and-Grasp Capability
1218521240190089 | 2026-09-16 |  | 2026-09-16 | Integrate Gripper / End-of-Arm Tooling | Phase 2 — Track & Grasp | [5 empty] | Objective: Integrate and configure the gripper or end-of-arm tooling required to grasp the tracked objects. Scope: Select or verify the appropriate tooling, establish the mechanical and control interfaces, and test the tooling under the planned operating conditions. Key Questions: • What gripper or end-of-arm tooling is required? • Is the tooling compatible with the robot and target objects? • How will the tooling be mounted and controlled? • What gripping parameters are required? • How will successful gripping be detected? • What safety constraints apply? Expected Output: A functional gripper or end-of-arm tooling setup ready for track-and-grasp experiments. Completion Criteria: The tooling is installed, configured, tested, and confirmed suitable for the planned grasping scenarios. | CynLr_EPM_PoC_Asana |  | Develop Track-and-Grasp Capability | Execute Grasping Experiments
1218521240190179 | 2026-09-16 |  | 2026-09-16 | Verify and Mount Gripper / Tooling | [8 empty] | Integrate Gripper / End-of-Arm Tooling
1218521240190180 | 2026-09-16 |  | 2026-09-16 | Configure Tooling Control | [8 empty] | Integrate Gripper / End-of-Arm Tooling
1218521240190181 | 2026-09-16 |  | 2026-09-16 | Test Gripper Operation | [8 empty] | Integrate Gripper / End-of-Arm Tooling
1218521240190091 | 2026-09-16 |  | 2026-09-16 | Execute Grasping Experiments | Phase 2 — Track & Grasp | [5 empty] | Objective: Execute the planned Phase 2 experiments to evaluate the integrated tracking-and-grasping capability. Scope: Run controlled experiments across the defined object, conveyor, tracking, and grasping scenarios while recording the required performance data. Key Questions: • Which experiment scenarios will be executed? • What operating conditions will be varied? • How will tracking and grasping outcomes be recorded? • What constitutes a successful grasp? • What failures or constraints must be documented? • Are the experiments repeatable? Expected Output: A complete set of experiment records containing tracking and grasping results, observations, and identified issues. Completion Criteria: Planned experiments are executed, required data is recorded, and deviations or failures are documented for analysis. | CynLr_EPM_PoC_Asana |  | Integrate Gripper / End-of-Arm Tooling | Evaluate Multi-Robot Coordination Feasibility
1218521240190182 | 2026-09-16 |  | 2026-09-16 | Prepare Experiment Setup | [8 empty] | Execute Grasping Experiments
1218521240190183 | 2026-09-16 |  | 2026-09-16 | Execute Grasping Trials | [8 empty] | Execute Grasping Experiments
1218521240190184 | 2026-09-16 |  | 2026-09-16 | Record Results and Document Failures | [8 empty] | Execute Grasping Experiments
1218521240190093 | 2026-09-16 |  | 2026-09-16 | Evaluate Multi-Robot Coordination Feasibility | Phase 2 — Track & Grasp | [5 empty] | Objective: Evaluate the feasibility of extending the Phase 2 tracking-and-grasping capability to coordinated operation involving multiple robots. Scope: Identify coordination requirements, potential interaction points, and constraints associated with multi-robot operation. Key Questions: • What role could multiple robots play in the system? • What information must be shared between robots? • How would task allocation and coordination work? • What timing and synchronization requirements exist? • What workspace and safety constraints apply? • What additional hardware or software would be required? Expected Output: A documented feasibility assessment identifying the requirements, constraints, and potential approach for multi-robot coordination. Completion Criteria: Multi-robot coordination requirements and constraints are documented, and the feasibility of a future implementation is assessed. | CynLr_EPM_PoC_Asana |  | Execute Grasping Experiments | Conduct Phase 2 Review
1218521240190185 | 2026-09-16 |  | 2026-09-16 | Define Multi-Robot Use Case | [8 empty] | Evaluate Multi-Robot Coordination Feasibility
1218521240190186 | 2026-09-16 |  | 2026-09-16 | Identify Coordination and Synchronization Requirements | [8 empty] | Evaluate Multi-Robot Coordination Feasibility
1218521240190187 | 2026-09-16 |  | 2026-09-16 | Document Feasibility Findings | [8 empty] | Evaluate Multi-Robot Coordination Feasibility
1218521240190095 | 2026-09-16 |  | 2026-09-16 | Conduct Phase 2 Review | Phase 2 — Track & Grasp | [5 empty] | Objective: Review the Phase 2 experiment results and determine whether the tracking-and-grasping capability meets the defined objectives and performance criteria. Scope: Evaluate experiment outcomes, identify limitations, document lessons learned, and determine the next steps for the project. Key Questions: • Were the Phase 2 objectives achieved? • How did tracking performance affect grasping? • What were the main failure modes? • Did the system meet the defined performance criteria? • What limitations remain? • What improvements or next steps are required? Expected Output: A Phase 2 review report summarizing results, limitations, lessons learned, and recommended next steps. Completion Criteria: Phase 2 results are reviewed, performance against the defined criteria is documented, and the next steps are agreed upon. | CynLr_EPM_PoC_Asana |  | Evaluate Multi-Robot Coordination Feasibility
1218521240190188 | 2026-09-16 |  | 2026-09-16 | Review Experiment Results | [8 empty] | Conduct Phase 2 Review
1218521240190189 | 2026-09-16 |  | 2026-09-16 | Evaluate Performance and Limitations | [8 empty] | Conduct Phase 2 Review
1218521240190190 | 2026-09-16 |  | 2026-09-16 | Document Lessons Learned and Next Steps | [8 empty] | Conduct Phase 2 Review
1218521240190191 | 2026-09-16 |  | 2026-09-16 | Integrate Robot, Conveyor, Camera, and RTU | Hardware & Integration | [5 empty] | Purpose: Integrate the robot, conveyor, camera, and RTU components required for the PoC. Activities: Confirm hardware interfaces and connection requirements. Connect the camera and sensing system. Connect the robot and conveyor system. Connect the RTU and robot controller. Configure communication interfaces. Perform an initial integrated-system check. Output: Integrated hardware setup ready for end-to-end communication and validation. | CynLr_EPM_PoC_Asana |  |  | Verify End-to-End Hardware Communication
1218521240190248 | 2026-09-16 |  | 2026-09-16 | Confirm hardware interfaces and connection requirements | [8 empty] | Integrate Robot, Conveyor, Camera, and RTU
1218521240190249 | 2026-09-16 |  | 2026-09-16 | Connect robot, conveyor, camera, and RTU components | [8 empty] | Integrate Robot, Conveyor, Camera, and RTU
1218521240190250 | 2026-09-16 |  | 2026-09-16 | Configure communication interfaces | [8 empty] | Integrate Robot, Conveyor, Camera, and RTU
1218521240190251 | 2026-09-16 |  | 2026-09-16 | Perform initial integrated-system check | [8 empty] | Integrate Robot, Conveyor, Camera, and RTU
1218521240190193 | 2026-09-16 |  | 2026-09-16 | Verify End-to-End Hardware Communication | Hardware & Integration | [5 empty] | Purpose: Verify that the robot, conveyor, camera, and RTU can communicate correctly as an integrated system. Activities: Verify communication between the camera and control software. Verify communication between the robot controller and control software. Verify communication between the conveyor, RTU, and robot. Check signal timing, data transfer, and command response. Record communication failures and required corrective actions. Output: Verified communication flow and documented interface issues. | CynLr_EPM_PoC_Asana |  | Integrate Robot, Conveyor, Camera, and RTU | Validate System Safety and Operational Readiness
1218521240190252 | 2026-09-16 |  | 2026-09-16 | Verify camera-to-software communication | [8 empty] | Verify End-to-End Hardware Communication
1218521240190253 | 2026-09-16 |  | 2026-09-16 | Verify robot-controller communication | [8 empty] | Verify End-to-End Hardware Communication
1218521240190254 | 2026-09-16 |  | 2026-09-16 | Verify conveyor and RTU communication | [8 empty] | Verify End-to-End Hardware Communication
1218521240190255 | 2026-09-16 |  | 2026-09-16 | Perform end-to-end communication test | [8 empty] | Verify End-to-End Hardware Communication
1218521240190195 | 2026-09-16 |  | 2026-09-16 | Validate System Safety and Operational Readiness | Hardware & Integration | [5 empty] | Purpose: Confirm that the integrated PoC system can operate safely and is ready for controlled experiments. Activities: Verify emergency-stop and safety mechanisms. Check robot, conveyor, camera, and RTU operating conditions. Confirm safe operating zones and movement limits. Verify that operators can start, stop, and reset the system safely. Record safety issues and required corrective actions. Confirm readiness before beginning experiments. Output: Safety and operational-readiness checklist with identified issues and corrective actions. | CynLr_EPM_PoC_Asana |  | Verify End-to-End Hardware Communication | Execute End-to-End Tracking and Grasping Tests
1218521240190256 | 2026-09-16 |  | 2026-09-16 | Verify emergency-stop and safety mechanisms | [8 empty] | Validate System Safety and Operational Readiness
1218521240190257 | 2026-09-16 |  | 2026-09-16 | Check operating conditions and movement limits | [8 empty] | Validate System Safety and Operational Readiness
1218521240190258 | 2026-09-16 |  | 2026-09-16 | Verify operator start, stop, and reset procedures | [8 empty] | Validate System Safety and Operational Readiness
1218521240190259 | 2026-09-16 |  | 2026-09-16 | Complete safety and operational-readiness checklist | [8 empty] | Validate System Safety and Operational Readiness
1218521240190197 | 2026-09-16 |  | 2026-09-18 | Define Test Cases and Success Criteria | Testing & Validation | [5 empty] | Purpose: Define the experiments required to evaluate the PoC against its objectives. Test cases: Track an object moving on a conveyor. Track objects with different shapes, sizes, and positions. Coordinate the robot with the moving object. Attempt to grasp an object while it is moving. Evaluate repeatability across multiple trials. Check safe and consistent system operation. Success criteria: Object tracking is demonstrated. Robot coordination with the moving object is demonstrated. Grasping performance is evaluated. Failures and limitations are recorded. Safety and operational issues are documented. | CynLr_EPM_PoC_Asana
1218521240190199 | 2026-09-16 |  | 2026-09-16 | Execute End-to-End Tracking and Grasping Tests | Testing & Validation | [5 empty] | Purpose: Execute the planned experiments and validate the complete system workflow. Execution steps: Confirm hardware, software, and test-environment readiness. Set up the robot, camera, conveyor, RTU, and gripper as required. Run tracking experiments with moving objects. Run grasping experiments where applicable. Record successful trials, failed trials, and unexpected behavior. Record safety issues, integration problems, and required adjustments. Output: Test records containing test case, setup, observed result, failure reason, and follow-up action. | CynLr_EPM_PoC_Asana |  | Validate System Safety and Operational Readiness | Measure Performance and Document Results
1218521240190201 | 2026-09-16 |  | 2026-09-16 | Measure Performance and Document Results | Testing & Validation | [5 empty] | Purpose: Measure PoC performance and document results for review and future decisions. Lead indicators: Test cases prepared Hardware and software readiness Calibration completed Integration issues resolved Experiments executed Open risks and blockers Lag indicators: Tracking success and failure results Grasping success and failure results Repeatability across trials Coordination performance Safety and operational issues Unresolved technical limitations Results to document: Expected versus observed behavior Successful and unsuccessful trials Root causes of failures Corrective actions Lessons learned Recommendations for the next phase Output: A results summary linked to the defined test cases and success criteria. | CynLr_EPM_PoC_Asana |  | Execute End-to-End Tracking and Grasping Tests
1218521240190203 | 2026-09-16 |  | 2026-09-18 | Identify Required External Resources | External Dependencies | [5 empty] | Purpose: Identify all external resources required to execute the PoC. Required resources: FANUC robot and controller access 7th-axis RTU and conveyor system Camera and sensing hardware Grippers and end-of-arm tooling Robot software, SDKs, and programming access Simulation or virtual-validation tools External manufacturing and machining support Output: A confirmed resource list showing availability, responsible team/vendor, expected availability date, and any constraints. Status: To be confirmed during planning. | CynLr_EPM_PoC_Asana
1218521240190205 | 2026-09-16 |  | 2026-09-18 | Track Hardware, Software, and Access Dependencies | External Dependencies | [5 empty] | Purpose: Track dependencies that may affect execution of Phase 1 and Phase 2. Dependencies to track: Robot and conveyor availability FANUC software and controller access RTU availability and integration information Camera and sensing-system access Gripper/tooling procurement Software libraries and development environments External vendor or manufacturing support Tracking information: Dependency, responsible party, required-by activity, current status, expected availability, and impact of delay. Output: Updated dependency register with open, resolved, or blocked status. | CynLr_EPM_PoC_Asana
1218521240190207 | 2026-09-16 |  | 2026-09-18 | Resolve Dependency Blockers | External Dependencies | [5 empty] | Purpose: Resolve external dependencies that may delay experiments, integration, or demonstrations. Process: Identify the blocked activity. Confirm the responsible team, vendor, or partner. Estimate the impact of the delay. Define a mitigation or fallback option. Escalate unresolved blockers during program reviews. Output: Blockers are either resolved, assigned an action owner, or documented with an agreed mitigation plan. | CynLr_EPM_PoC_Asana |  | Coordinate Team Activities and Reviews
1218521240190209 | 2026-09-16 |  | 2026-09-18 | Track Project Progress and Milestones | Program Management | [5 empty] | Purpose: Track the overall progress of the PoC against planned milestones, deliverables, and success criteria. Activities: Review task completion and milestone progress. Identify delayed, blocked, or at-risk activities. Compare planned versus actual progress. Track phase-gate readiness. Escalate issues requiring management attention. Output: Updated project status showing completed work, ongoing activities, delays, blockers, and upcoming milestones. | CynLr_EPM_PoC_Asana |  |  | Coordinate Team Activities and Reviews
1218521240190211 | 2026-09-16 |  | 2026-09-16 | Coordinate Team Activities and Reviews | Program Management | [5 empty] | Purpose: Coordinate activities across software, robotics, mechanical, electronics, vision, and external partner teams. Coordination activities: Confirm inputs and outputs required between disciplines. Identify handoffs between hardware, software, and integration teams. Review technical progress and unresolved issues. Coordinate access to robots, cameras, conveyors, RTU, and testing facilities. Escalate cross-functional blockers. Conduct phase-gate reviews before moving to the next phase. Review points: Phase 1 experiment-definition review Phase 1 integration review Phase 1 results review Phase 2 integration review Final PoC review Output: Coordinated action list with responsible owners, dependencies, decisions, and next steps. | CynLr_EPM_PoC_Asana |  | Track Project Progress and Milestones | Maintain Project Documentation and Status Updates,Resolve Dependency Blockers
1218521240190213 | 2026-09-16 |  | 2026-09-16 | Maintain Project Documentation and Status Updates | Program Management | [5 empty] | Purpose: Maintain a single, up-to-date record of project progress, decisions, risks, dependencies, and experiment results. Documentation to maintain: Project plan and task status Milestone progress Risk and dependency registers Key decisions and open issues Experiment plans and results Meeting notes and action items Final findings and recommendations Status update format: Overall status: Not Started / In Progress / Blocked / Completed Completed activities Activities in progress Next planned activities Current blockers and risks Decisions required Output: Regular status updates and a complete project record that can be used for reviews and handover. | CynLr_EPM_PoC_Asana |  | Coordinate Team Activities and Reviews
1218521240190312 | 2026-09-16 |  | 2026-09-18 | Define KPIs and Progress-Balancing Schemes | Program Management | [5 empty] | Purpose: Define measurable indicators and management mechanisms to minimize delays, coordination problems, and wasted effort while maximizing the outcome of the CynLr robotics PoC. External Dependencies KPI: Number of unresolved external blockers Average dependency resolution time Percentage of critical dependencies resolved before the required milestone Measurement: Track each dependency with an owner, due date, status, and escalation date. 2. Research Work KPI: Research milestones completed Time taken to validate a technical approach Number of unresolved research questions Measurement: Review research outputs and technical decisions at defined checkpoints. 3. Development Work KPI: Development tasks completed Integration defects identified and resolved Percentage of planned development milestones completed Measurement: Compare planned versus completed tasks and track unresolved technical issues. 4. Project Infrastructure Setup KPI: Robot, camera, conveyor, RTU, gripper, and software readiness Number of infrastructure blockers Percentage of required setup activities completed Measurement: Use a readiness checklist before integration and testing. 5. Testing and Validation KPI: Test-case completion rate Object-tracking success rate Grasping success rate End-to-end test success rate Number of critical defects Measurement: Compare test results against predefined success criteria. 6. Delivery KPI: Milestone completion rate Deliverables completed Number of unresolved critical issues at handover Final PoC acceptance status Measurement: Use a final delivery checklist and review all open issues before handover. Lead Indicators: Hardware and software readiness Completion of calibration Test cases defined Dependencies assigned to owners Blockers resolved within agreed timelines Milestones completed as planned Lag Indicators: Tracking performance Grasping performance End-to-end system reliability Final PoC acceptance Completion of agreed deliverables Progress-Balancing / Reward-Loss Scheme: Recognize teams for completing milestones, resolving dependencies early, and meeting agreed quality criteria. Escalate delayed or blocked activities during program reviews. Reassess estimates and reallocate resources when bottlenecks affect critical milestones. Do not evaluate success only by task completion; consider quality, integration readiness, and technical outcomes together. | CynLr_EPM_PoC_Asana
1218606664348947 | 2026-09-18 |  | 2026-09-18 | Define KPIs for Technical Performance | [8 empty] | Define KPIs and Progress-Balancing Schemes
1218606664348948 | 2026-09-18 |  | 2026-09-18 | Define KPIs for Research, Development, and Infrastructure | [8 empty] | Define KPIs and Progress-Balancing Schemes
1218606664348949 | 2026-09-18 |  | 2026-09-18 | Define Lead and Lag Indicators | [8 empty] | Define KPIs and Progress-Balancing Schemes
1218606664348950 | 2026-09-18 |  | 2026-09-18 | Define Progress-Balancing and Escalation Mechanism | [8 empty] | Define KPIs and Progress-Balancing Schemes
1218521240190215 | 2026-09-16 |  | 2026-09-18 | Identify Technical and Operational Risks | Risks & Decisions | [5 empty] | Key risks identified from the PoC context: Limited simulation and virtual-validation capability Dependence on external hardware manufacturing and machining Delays in procurement of imported components Limited robot kinematic libraries for real-time multi-robot coordination Possible limitations in FANUC software access or support Difficulty achieving reliable tracking and grasping of moving or variable objects Output: Risk register containing risk description, affected activity, impact, likelihood, trigger, and responsible owner. | CynLr_EPM_PoC_Asana
1218521240190217 | 2026-09-16 |  | 2026-09-18 | Evaluate Risks and Define Mitigation Actions | Risks & Decisions | [5 empty] | Risk evaluation approach: Each risk will be assessed based on its likelihood and impact on schedule, cost, technical feasibility, and PoC success. Mitigation examples: Confirm hardware availability early. Track procurement lead times and identify alternatives. Use available simulation tools while documenting their limitations. Validate robot coordination requirements before integration. Engage FANUC support when software or controller access becomes a blocker. Begin with controlled experiments before increasing object or motion complexity. Output: Prioritized risk list with mitigation actions, owners, and review dates. | CynLr_EPM_PoC_Asana |  |  | Document Key Decisions and Open Issues
1218521240190219 | 2026-09-16 |  | 2026-09-16 | Document Key Decisions and Open Issues | Risks & Decisions | [5 empty] | Decisions to document: Which capabilities are included in the Phase 1 PoC? What criteria must be met before starting Phase 2? Which robot, conveyor, RTU, camera, and gripper configuration will be used? Which software tools and robot interfaces will be adopted? What level of multi-robot coordination will be evaluated? Open issues: Final resource availability External vendor timelines Acceptance criteria and performance targets FANUC software/support availability Required simulation and validation capability Output: Decision log containing the decision, date, stakeholders, rationale, and resulting action. | CynLr_EPM_PoC_Asana |  | Evaluate Risks and Define Mitigation Actions
1218521240190288 | 2026-09-16 |  | 2026-09-18 | Identify Required Resources | Resource & Effort Planning | [5 empty] | Purpose: Identify the people, equipment, software, and facilities required for the PoC. Resource categories: Robotics and controls engineering Computer vision and software engineering Mechanical engineering Electronics and electrical engineering Program management External manufacturing and integration partners Equipment and tools: FANUC robot and controller 7th-axis RTU Conveyor system Camera and sensing hardware Gripper and end-of-arm tooling Robot software, SDKs, and simulation tools Output: Resource list with availability, responsible team, location, and constraints. | CynLr_EPM_PoC_Asana
1218521240190292 | 2026-09-16 |  | 2026-09-18 | Estimate Skill Hours | Resource & Effort Planning | [5 empty] | Purpose: Estimate the effort required for major activities and subtasks. Effort categories: Robotics and controls Computer vision and software Mechanical and tooling Electronics and integration Testing and validation Program management For each activity, record: Activity or subtask Resource category Estimated skill hours Location Responsible team or owner Dependencies Assumptions Note: Estimates will be refined during detailed planning. | CynLr_EPM_PoC_Asana |  |  | Map Resources to Activities
1218521240190298 | 2026-09-16 |  | 2026-09-16 | Estimate effort for Phase 1 activities | [8 empty] | Estimate Skill Hours
1218521240190299 | 2026-09-16 |  | 2026-09-16 | Estimate effort for Phase 2 activities | [8 empty] | Estimate Skill Hours
1218521240190300 | 2026-09-16 |  | 2026-09-16 | Estimate effort for Hardware and Integration activities | [8 empty] | Estimate Skill Hours
1218521240190301 | 2026-09-16 |  | 2026-09-16 | Estimate effort for Testing and Validation activities | [8 empty] | Estimate Skill Hours
1218521240190302 | 2026-09-16 |  | 2026-09-16 | Estimate effort for Program Management activities | [8 empty] | Estimate Skill Hours
1218521240190294 | 2026-09-16 |  | 2026-09-16 | Map Resources to Activities | Resource & Effort Planning | [5 empty] | Purpose: Map the required resource categories and estimated effort to the project activities. Activities to map: Experiment definition Resource verification Camera and robot setup Calibration Tracking development Robot and RTU integration Track-and-grasp development Testing and validation Results analysis Final review Output: Activity-level resource and effort mapping showing which skills are required for each task. | CynLr_EPM_PoC_Asana |  | Estimate Skill Hours | Review Resource Constraints and Costs
1218521240190296 | 2026-09-16 |  | 2026-09-16 | Review Resource Constraints and Costs | Resource & Effort Planning | [5 empty] | Purpose: Identify resource constraints and cost-related considerations that may affect the PoC schedule and execution. Review: Hardware availability External manufacturing and procurement lead times Robot, RTU, and software access Availability of engineering skills Testing-facility access External vendor support Potential additional tooling or equipment costs Output: Resource constraint and cost-observation summary with mitigation actions where required. | CynLr_EPM_PoC_Asana |  | Map Resources to Activities
1218521240190221 | 2026-09-16 |  | 2026-09-16 | Review Overall PoC Results | Final Review | [5 empty] | Purpose: Review the overall results from Phase 1 and Phase 2 against the agreed PoC objectives and success criteria. Review areas: Moving-object tracking performance Robot and conveyor coordination Track-and-grasp performance System repeatability and consistency Safety and operational readiness Integration issues and unresolved technical limitations Resource usage, schedule performance, and major blockers Output: Consolidated results review showing achieved objectives, partially achieved objectives, failures, and remaining gaps. | CynLr_EPM_PoC_Asana |  | Conduct Phase 1 Review,Define Phase 2 Experiment | Document Final Findings and Recommendations
1218521240190223 | 2026-09-16 |  | 2026-09-16 | Document Final Findings and Recommendations | Final Review | [5 empty] | Purpose: Document the final technical and program-level findings from the PoC. Document: What was successfully demonstrated What could not be demonstrated Main technical limitations Major risks encountered Resource and cost observations Lessons learned Recommendations for further development Conditions required for future production-scale implementation Output: Final findings and recommendations document supporting the decision on the next stage of development. | CynLr_EPM_PoC_Asana |  | Review Overall PoC Results | Prepare Final Demonstration and Handover
1218521240190225 | 2026-09-16 |  | 2026-09-16 | Prepare Final Demonstration and Handover | Final Review | [5 empty] | Purpose: Prepare the final PoC demonstration and hand over the project information to relevant stakeholders. Handover contents: Final demonstration agenda Demonstration setup and prerequisites Recorded results and evidence Project plan and task status Risk and dependency register Key decisions and open issues Final findings and recommendations Next-step action items Output: Completed final demonstration, organized project records, and clearly assigned follow-up actions. | CynLr_EPM_PoC_Asana |  | Document Final Findings and Recommendations