## Activity & Effort Plan
Activity | Description | Sub-Activity | Resource Category | Effort (Hours) | Location
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Define Phase 1 experiment | Program Manager | 4 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Verify robot and conveyor availability | Robotics Engineer | 4 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Prepare camera and sensing setup | Vision Engineer | 12 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Calibrate camera and coordinate system | Vision Engineer | 16 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Develop object-tracking capability | Vision / ML Engineer | 40 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Integrate tracking output with robot | Robotics / Software Engineer | 24 | CynLr
Phase 1 – Track Moving Objects | Demonstrate tracking of moving objects using a robot, camera, and conveyor | Execute tracking experiments | Robotics / Vision Team | 24 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Define Phase 2 experiment | Program Manager | 4 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Confirm RTU and robot availability | Robotics Engineer | 4 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Prepare RTU integration setup | Robotics / Mechanical Engineer | 20 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Integrate robot and RTU | Robotics Engineer | 40 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Develop track-and-grasp capability | Robotics / ML Engineer | 60 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Integrate gripper or end-of-arm tooling | Mechanical / Robotics Engineer | 32 | CynLr
Phase 2 – Track & Grasp | Demonstrate tracking and grasping of moving objects using robot freedom and RTU | Execute grasping experiments | Robotics / Vision Team | 32 | CynLr
Hardware & Integration | Integrate and validate the complete hardware setup | Integrate robot, conveyor, camera, and RTU | Robotics / Electronics Engineer | 40 | CynLr
Hardware & Integration | Integrate and validate the complete hardware setup | Verify end-to-end hardware communication | Electronics / Software Engineer | 24 | CynLr
Hardware & Integration | Integrate and validate the complete hardware setup | Validate system safety and operational readiness | Robotics / Safety Engineer | 16 | CynLr
Testing & Validation | Verify technical performance and document results | Define test cases and success criteria | Program Manager / Technical Leads | 8 | CynLr
Testing & Validation | Verify technical performance and document results | Execute end-to-end tracking and grasping tests | Cross-functional Team | 32 | CynLr
Testing & Validation | Verify technical performance and document results | Measure performance and document results | Test / Data Engineer | 24 | CynLr
External Dependencies | Track dependencies outside the immediate project team | Coordinate with hardware manufacturing partners | Program Manager / External Vendor | 12 | External
External Dependencies | Track dependencies outside the immediate project team | Track procurement of imported components | Procurement / Finance Team | 12 | CynLr / External
External Dependencies | Track dependencies outside the immediate project team | Coordinate robot kinematic library support | Robotics / Software Engineer | 16 | CynLr
External Dependencies | Track dependencies outside the immediate project team | Coordinate FANUC support | Robotics / Vendor Support | 12 | CynLr / External
Risks & Decisions | Identify, monitor, and mitigate project risks | Review simulation and virtual validation limitations | Program Manager / Technical Leads | 8 | CynLr
Risks & Decisions | Identify, monitor, and mitigate project risks | Review procurement and manufacturing risks | Program Manager / Procurement | 8 | CynLr
Program Management | Manage planning, coordination, and reporting | Weekly progress tracking and coordination | Program Manager | 24 | CynLr
Program Management | Manage planning, coordination, and reporting | Maintain risks, decisions, and dependencies | Program Manager | 16 | CynLr
Final Review | Consolidate results and prepare the final demonstration | Review overall PoC results | Program Manager / Technical Leads | 8 | CynLr
Final Review | Consolidate results and prepare the final demonstration | Document findings and recommendations | Program Manager / Technical Leads | 12 | CynLr
Final Review | Consolidate results and prepare the final demonstration | Prepare final demonstration and handover | Cross-functional Team | 16 | CynLr
604
Note: Effort values are preliminary person-hour estimates intended for planning and complexity assessment. Actual effort may vary depending on hardware availability, external dependencies, integration issues, and experimental results.

## KPI & Success Metrics
Category | KPI | Measurement Method | Target / Success Criteria | Indicator Type | Owner | Review Cadence | Linked Activity
External Dependencies | Number of unresolved external blockers | Track dependency status, owner, due date and escalation date | Critical blockers resolved or escalated before milestone impact | Lead | Program Manager | Weekly | External Dependencies
External Dependencies | Average dependency resolution time | Record blocker identification and resolution dates | Minimize resolution time for critical dependencies | Lead | Program Manager | Weekly | External Dependencies
External Dependencies | Critical dependencies resolved before milestone | Compare dependency resolution date against required milestone | Critical dependencies resolved before milestone | Lead | Program Manager | Weekly | External Dependencies
Research Work | Research milestones completed | Track planned vs completed research milestones | Planned research milestones completed | Lead | Technical Leads | Phase Reviews | Phase 1 / Phase 2
Research Work | Time to validate technical approach | Record start and validation completion dates | Technical approaches validated within planned timeframe | Lead | Technical Leads | Phase Reviews | Phase 1 / Phase 2
Research Work | Unresolved research questions | Maintain research-question/decision log | Reduce unresolved questions before integration | Lead | Technical Leads | Weekly | Risks & Decisions
Development Work | Development tasks completed | Compare planned vs completed development tasks | Planned development milestones completed | Lead | Engineering Leads | Weekly | Phase 1 / Phase 2
Development Work | Integration defects identified and resolved | Track defects through identification and closure | Critical integration defects resolved before testing | Lag | Engineering Leads | Weekly | Hardware & Integration
Development Work | Planned development milestones completed | Compare planned and actual milestone completion | Milestones completed according to plan | Lead | Program Manager | Weekly | Program Management
Infrastructure Setup | Robot/camera/conveyor/RTU/gripper/software readiness | Readiness checklist | Required infrastructure ready before integration/testing | Lead | Engineering Leads | Before Integration | Hardware & Integration
Infrastructure Setup | Number of infrastructure blockers | Track setup blockers and status | Critical blockers resolved before integration | Lead | Program Manager | Weekly | Hardware & Integration
Infrastructure Setup | Setup activities completed | Compare planned vs completed setup activities | Required setup activities completed | Lead | Engineering Leads | Weekly | Hardware & Integration
Testing & Validation | Test-case completion rate | Completed test cases / planned test cases | Test cases completed against defined plan | Lead | Test / Data Engineer | Test Reviews | Testing & Validation
Testing & Validation | Object-tracking success rate | Successful tracking trials / total tracking trials | Meet predefined tracking success criteria | Lag | Vision / ML Team | Experiment Review | Phase 1
Testing & Validation | Grasping success rate | Successful grasps / total grasping trials | Meet predefined grasping success criteria | Lag | Robotics Team | Experiment Review | Phase 2
Testing & Validation | End-to-end test success rate | Successful end-to-end tests / total tests | Meet predefined end-to-end criteria | Lag | Cross-functional Team | Final Testing | Testing & Validation
Testing & Validation | Number of critical defects | Track critical defects during testing | No unresolved critical defects at handover | Lag | Engineering Leads | Test Reviews | Testing & Validation
Delivery | Milestone completion rate | Completed milestones / planned milestones | Planned milestones completed | Lead | Program Manager | Weekly / Final | Program Management
Delivery | Deliverables completed | Track required deliverables | Agreed deliverables completed | Lag | Program Manager | Final Review | Final Review
Delivery | Unresolved critical issues at handover | Review open issue register | No unresolved critical issues at handover | Lag | Program Manager | Final Review | Final Review
Delivery | Final PoC acceptance status | Final technical and program review | Acceptance against agreed PoC criteria | Lag | Program Manager / Technical Leads | Final Review | Final Review